## Schedule
|  | Year | Doc # | 2002 | 2003 | 2004 | 2004 | 2004 | 2004 | 2004 | 2005 | 2005 | 2005 | 2005 | 2005 | 2006 | 2006 | 2006 | 2006 | 2006 | 2007 | 2007 | 2007 | 2007 | 2008 | 2008 | 2008 | 2008 | 2009 | 2009 | 2009 | 2009 | 2010 | 2010 | 2010 | 2010
|  | Meeting |  |  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
|  | Date |  |  | Nov | Feb | April | June | August | November | February | April 11-15 | June 20-24 | Sept 12-16 | Dec 5-9 | Feb 13-17 | April 24-28 | June 26-30 | Sept 25-29 | Dec 4-8 | March 26-30 | June 25-29 | Sept 24-28 | Dec 10-14 | Mar 10-14 | June 23-27 | Sept 22-26 | Dec 8-12 | Mar 10-14 | June 23-27 | Sept 22-26 | Dec 7-11 | March 22-26 | June 21-25 | Sept 20-24 | Dec 6-10
|  | Location |  |  | London | Anaheim | St Louis | Orlando | Montreal | Washington | Burlingame | Athens | Boston | Atlanta | Burlingame | Tampa | St Louis | Boston | Anaheim | Washington | San Diego | Brussels | Jacksonville | Burlingame | Washington | Ottawa | Orlando | Santa Clara | Washington | San Jose CR | San Antonio, TX | Long Beach, CA | Jacksonville, FL | Minneapolis MN | Cambridge MA | Santa Clara CA
|  | Events |  |  | Nov: Coalition day; 5 November: Coalition day | [8 empty] | Info. day | [5 empty] | Info. day
SE DSIG
| UML Profile for DoDAF/MoDAF | [12 empty] | Issued 16 Sept |  | LoI - 23 Feb | Initial Submission - 5 June |  |  | Revised Submission - 5 Mar 2007 |  | Recommend Adoption |  |  |  |  | Issue RFC | bar: 1 February
|  | UPDM 2.0 | [28 empty] | Issue | LOI |  | Initial | Revised | Vote Recommend Adoption | bar: 1 February
Shared Operational Picture Exchange Services
| Information Exchange Mechanism |  | 04-06-28 | RFI | 2 April: Draft |  | postponed 2 ODS NII signed up | LoI - 05 Dec | MOVED TO MARS | [11 empty] | Discussion
| Policy & Rules Management Services |  |  |  | 4 August: New Business |  | Draft issued 22 Aug | LoI - 5 Dec | MOVED TO MARS
| Emergency Management | [25 empty] | Discussion | bar: 4 August to 1 February
| Information Exchange Data Model |  | 04-06-27 |  | Nov: RFI; 2 April: Draft |  | postponed 2 ODS NII signed up | LoI - 05 Dec | [7 empty] | Initial Submission - 3 Sep 2007 |  |  |  | Revised Submissions | [5 empty] | Vote Recommend Adoption |  |  | FTF
Combat Management Systems
C4I Infrastructure Services
| Application Management |  | 04-06-26 |  | Nov: New Business; 2 April: Draft; 5 November: LoI | Initial 05-05-30 | [7 empty] | Revised Submission - 5 Mar 2007 | Recommend Adoption |  |  |  | FTF report |  |  |  | FTF report |  |  |  | FTF2 report
|  | Dynamic AMSM | [23 empty] | new business
|  | Co-operating AMSM | [23 empty] | new business
|  | UML Profile for AMSM | [23 empty] | new business
|  | Instrumentation for AMSM | [23 empty] | new business
| Alert Management |  | 04-11-13 |  | 3 June: New Business; 4 August: Draft | LOI 05-05-30 |  | Initial Submission - 14 Nov | [9 empty] | Revised Submission - 4 Jun 2007 | Recommend Adoption |  |  |  | FTF report
| Role Management |  |  |  | 1 Feb: New Business | [5 empty] | discussions
| Application Instrumentation |  |  |  | 3 June: New Business |  | Link with SDO |  | Draft
| GEOSIT/TACSIT RFI |  |  |  | 1 February: New Business |  | scoping meeting | [6 empty] | Issue RFI
|  | TACSIT Control Interface | [15 empty] | scoped | [5 empty] | LOI | Initial Submission |  |  | revised submission | [5 empty] | Vote Recommend Adoption
TACSIT Map Interface
|  | TACSIT Tactical Info & Track Interface | [25 empty] | ? Draft
TACSIT Geometric Interface
|  | TACSIT Configuration Interface | [25 empty] | ? Draft
| Common Information Model for CMS |  |  |  | 5 November: New Business
Application Deployment
Platform Infrastructure Administration
Platform Operations Monitoring & Control
C4I Infrastructure Services Profiles
C4I Middleware Profiles
C4I Transport Profiles
C4I O/S and Hardware Support Measures
C4I Domain Application Services
Sensor Data Acquisition
|  | Generic Sonar Interface | [16 empty] | withdrawn
|  | Generic Radar Interface |  |  | 3 June: RFI | [8 empty] | being worked upon external to OMG
|  | Generic Sensor Interface | [13 empty] | Initial Submission | Revised Submissions |  |  | Adoption
| Ships Navigational Data (NNSI) | [18 empty] | discussions |  |  |  | RFP Issued |  | LOI | Initial Submission |  |  |  | revised submission |  |  | Vote Recommend Adoption
| Meteorological & Oceanographic | [23 empty] | RFP Issued |  | LOI |  |  |  | Initial Submission |  |  |  | revised submission | Vote Recommend Adoption
Tactical Analysis
Tactical Control
Strategic Analysis
Simulation & Planning
Logistics
Organization Control
Training
Profile and Policy Management
| Data Tagging & Labelling RFI | [19 empty] | discussions |  | Issue RFI |  |  | RFI responses | RFI responses | [8 empty] | RFP Issued | LOI
Security Posture Management
Security Object Services
Secure Common Object Services
Secure Data Distribution Services
Secure Component Model
C4I Notional Architecture
| Architecture scoping |  |  |  | 1 Feb: Draft
Integration Aids
| Automated Test Re Test Case Exchange | [23 empty] | Draft RFI | RFI |  | RFI responses | [5 empty] | RFP Issued |  | LOI | Initial Submission | revised submission | Vote Recommend Adoption